Development Plan for a Multimodal Electronic Parts Recognition System

VDI 2220 product planning and VDI 2221 development roadmap

Project purpose

Design and validate a professional PC based inspection system that recognizes electronic parts from high resolution visible images, near infrared reflectance and radiometric thermal behaviour. The STM32 acquisition head supplies synchronized sensor data; the computer performs recognition, temporal fusion, supervised learning and data management.

Author  Dereje Hailemariam

Version  1.0

Date  22 September 2026

Status  Project planning baseline

# Document control

| Field | Entry |
| --- | --- |
| Document owner | Dereje Hailemariam |
| Intended readers | Project owner, engineering partners, potential pilot users and funding partners |
| Decision supported | Approval and execution of a staged prototype and product validation programme |
| Planning horizon | Twelve to eighteen months depending on team size |
| Primary development platform | STM32N6570 DK acquisition prototype and Windows PC software |
| Review cycle | At every development gate and at least monthly during active work |

# Executive summary

The proposed product is a bench oriented inspection system for electronic repair and engineering laboratories. A compact STM32 acquisition head captures a macro RGB image, an 850 nm near infrared image and a radiometric thermal frame at a controlled working distance. It sends synchronized raw data to a Windows computer. The PC application detects components, reads markings, classifies package types, measures component temperatures and learns from technician corrections.

The realistic first release will not include SWIR, hyperspectral imaging, Raman spectroscopy or XRF. These methods are technically useful but would multiply cost, calibration effort and regulatory work before the central customer problem has been validated. The mechanical and software architecture will nevertheless allow later PC connected modules.

The recommended development route begins with the STM32N6570 DK, a 5 MP macro camera and FLIR Lepton 3.5. A commercial product decision should not be made until repair technicians confirm that the system reduces fault localization time and that thermal resolution is adequate. A 256 by 192 or 320 by 256 radiometric core should be evaluated before the production design is frozen.

## Project decision

| Decision | Recommendation | Reason |
| --- | --- | --- |
| Product form | Bench instrument with adjustable stand | Fixed distance improves focus, spectral repeatability and RGB thermal alignment |
| Processing location | Windows PC | Allows larger models, retraining, databases and easier software iteration |
| Embedded role | Sensor control and synchronized streaming | Keeps firmware deterministic and reduces embedded AI risk |
| V1 spectral channels | RGB, 850 nm NIR and LWIR thermal | These channels address recognition, markings and heating with manageable cost |
| Learning method | Supervised continual learning | User corrections improve the system without uncontrolled autonomous retraining |

# Contents

1 Product opportunity and scope

2 User needs and use cases

3 Product planning process

4 Product requirements

5 System architecture

6 Sensor and illumination concept

7 Embedded acquisition head

8 PC software and learning architecture

9 Dataset and model development

10 Calibration and measurement quality

11 Verification and pilot testing

12 Safety compliance and data protection

13 Work packages schedule and gates

14 Cost plan and market validation

15 Risk management

16 Immediate actions

Appendices

# 1 Product opportunity and scope

## 1.1 Problem statement

Technicians often identify faults by combining visual inspection, measurements and a separate thermal camera. Low cost thermal cameras show where heat appears but may not identify the exact component. Conventional image recognition can identify a package or marking but does not explain whether the component is operating normally. The project will combine these observations in one documented workflow.

## 1.2 Product objective

The objective is to build a professional inspection aid that can locate electronic parts, propose their class and package, read visible markings, assign thermal measurements to the detected parts and retain confirmed knowledge for future inspections.

## 1.3 V1 scope

Stationary or stand mounted inspection of unpowered and powered circuit boards.

High resolution RGB macro capture for component detection and optical character recognition.

Controlled 850 nm near infrared capture for additional marking and material contrast.

Radiometric thermal capture for hotspot and heating rate measurement.

Distance sensing, controlled illumination and repeatable image registration.

Windows application for acquisition, annotation, recognition, supervised learning and reporting.

User confirmation and correction workflow with model versioning and rollback.

## 1.4 Explicitly excluded from V1

Exact identification of every unmarked electronic component.

Electrical value recognition where the value is not optically encoded.

Autonomous diagnosis without technician confirmation.

Integrated SWIR, hyperspectral, Raman, FTIR, XRF or X ray instrumentation.

Medical temperature measurement or safety critical decisions.

Cloud dependent processing or mandatory remote image upload.

A handheld battery product before the bench workflow has been validated.

## 1.5 Future options

The architecture should reserve interfaces for 365 nm fluorescence imaging, a small visible and near infrared point spectrometer, a higher resolution thermal core and external laboratory instruments. These additions require separate business and technical justification.

# 2 User needs and use cases

## 2.1 Primary users

| User group | Current task | Expected benefit |
| --- | --- | --- |
| Independent repair technician | Find shorts and overheating parts | Faster localization and clearer component identity |
| Industrial electronics service | Compare failed and known good boards | Repeatable records and thermal comparison |
| Development laboratory | Observe component behaviour during tests | Combined visual and temperature timeline |
| Technical education | Explain component function and failure | Traceable examples and guided inspection |

## 2.2 Core use cases

1.  Place a PCB under the camera, select the board area and obtain a component map.

2.  Click a component to view class, package, OCR result, confidence and temperature history.

3.  Power the PCB through normal laboratory equipment and monitor heating over time.

4.  Compare the current board with a stored reference board or an earlier inspection.

5.  Correct a wrong component label and store the confirmed example for future learning.

6.  Export an inspection report containing images, component regions, measurements and notes.

## 2.3 User research before design freeze

Interview at least fifteen repair professionals and observe five real repair sessions. The interviews must establish the smallest relevant component, normal working distance, required temperature accuracy, acceptable setup time, preferred report format and willingness to pay. At least five users should test the alpha system before the first custom PCB is approved.

# 3 Product planning process

VDI 2220 covers product planning, while VDI 2221 provides a structured model for developing technical products and systems. This project uses VDI 2220 to establish the opportunity and product definition, then continues with VDI 2221 for implementation and verification [1] [2].

| Stage | Main activities | Required output | Gate |
| --- | --- | --- | --- |
| Situation analysis | Users, alternatives, technical constraints and price | Validated problem statement | G0 |
| Product ideas | Bench, handheld and hybrid concepts | Concept comparison | G1 |
| Product definition | Requirements, target price and V1 scope | Approved product specification | G2 |
| System design | Functions, interfaces, optics and software | Architecture baseline | G3 |
| Prototype validation | Acquisition, calibration and baseline recognition | Working alpha system | G4 |
| Design validation | Field tests, reliability and compliance | Pilot ready design | G5 |
| Production validation | Pilot build, yield and support process | Launch decision | G6 |

## 3.1 Gate rules

A gate is passed only when its measurable criteria and evidence are available. A technical demonstration alone does not justify production. Customer benefit, cost, safety and maintainability must be reviewed together.

# 4 Product requirements

## 4.1 Functional requirements

| ID | Requirement | Priority | Acceptance evidence |
| --- | --- | --- | --- |
| FR 01 | Capture a full resolution RGB macro image | Must | Image saved with exposure and focus metadata |
| FR 02 | Capture an 850 nm NIR image from the same board area | Must | Registered NIR frame is available |
| FR 03 | Capture raw radiometric thermal data | Must | Temperature data retained for every pixel |
| FR 04 | Associate sensor frames using one frame set identifier | Must | No ambiguous frame pairing |
| FR 05 | Measure camera to board distance | Must | Distance stored with every detailed capture |
| FR 06 | Detect supported component classes | Must | Bounding box class and confidence returned |
| FR 07 | Classify supported package types | Should | Package and confidence returned |
| FR 08 | Read visible package markings | Should | OCR text and alternatives returned |
| FR 09 | Assign temperature statistics to components | Must | Maximum average and trend displayed |
| FR 10 | Allow technician confirmation and correction | Must | Correction stored with provenance |
| FR 11 | Create a versioned learning dataset | Must | Training records can be reproduced |
| FR 12 | Export inspection results | Should | PDF or HTML report and raw project archive |

## 4.2 Performance requirements

| Parameter | Prototype target | Product target |
| --- | --- | --- |
| RGB still image | At least 5 MP | 5 to 12 MP |
| RGB live view | At least 720p at 10 fps | 720p at 15 fps or better |
| Thermal resolution | 160 by 120 | At least 256 by 192 preferred |
| Working distance | 80 to 200 mm | Defined calibrated range |
| Registration error | At most 3 thermal pixels | At most 2 thermal pixels |
| Supported component recall | At least 80 percent | At least 90 percent |
| Unknown rejection | Demonstrated | False identity below 5 percent |
| Detailed result latency | Below 3 seconds | Below 1 second on target PC |
| Continuous session | 30 minutes | At least 4 hours |

## 4.3 Quality requirements

The application must retain raw source data and never overwrite it with processed images.

Every model result must include a confidence value and model version.

Low confidence results must be presented as unknown or as ranked alternatives.

A failed model update must be reversible without losing inspection projects.

Calibration profiles must be identified by device serial number and date.

The software must run locally without an internet connection after installation.

# 5 System architecture

The acquisition head performs deterministic sensor control and packaging. The PC owns image processing, recognition, learning and storage. This boundary allows rapid model changes without redesigning the embedded device.

Figure 1  Proposed product architecture

## 5.1 Frame set

The basic data object is a synchronized frame set. It contains the RGB image, NIR image, raw thermal frame, timestamp, distance, exposure, illumination state, focus position, ambient measurements and calibration identifiers. The PC rejects incomplete or mismatched frame sets rather than guessing.

| Data group | Fields |
| --- | --- |
| Identity | Device ID, session ID, frame set ID and timestamp |
| RGB | Image, exposure, gain, focus and white balance |
| NIR | Image, wavelength, LED current, exposure and gain |
| Thermal | Raw values, calibration mode, shutter status and sensor temperature |
| Geometry | Distance, camera pose when available and calibration profile |
| Environment | Ambient temperature, humidity and illumination status |

# 6 Sensor and illumination concept

## 6.1 V1 sensor selection

| Channel | Prototype choice | Purpose | Decision before product design |
| --- | --- | --- | --- |
| RGB | 5 MP MIPI camera with M12 macro lens | Shape, colour, markings and OCR | Confirm optical sharpness at 80 to 200 mm |
| NIR | Same camera with removable IR cut or dedicated mono NIR sensor | Additional contrast at 850 nm | Compare shared and separate camera designs |
| Thermal | FLIR Lepton 3.5 | Radiometric proof of concept | Evaluate 256 by 192 and 320 by 256 cores |
| Distance | Time of flight sensor | Focus and registration correction | Verify against board reflectivity |
| Environment | Temperature and humidity sensor | Record operating conditions | Select calibrated part if compensation needs it |

## 6.2 Illumination

Dimmable high CRI white LED ring for RGB imaging.

850 nm NIR LED ring driven by a constant current driver and synchronized strobe.

Four independently controlled LED sectors to reveal package markings under different angles.

Diffuser for uniform illumination and cross polarizers to suppress glare.

Photodiode feedback to detect illumination drift and prevent saturation.

## 6.3 Deferred spectral options

A 365 nm UV fluorescence mode is a reasonable second phase because it may reveal flux, coatings and contamination. It requires an enclosure interlock, UV blocking optics and a validated customer use case. A compact 340 to 850 nm point spectrometer can be assessed after the image based workflow works. Direct UV, SWIR and hyperspectral cameras remain research options because their cost and optical requirements are much higher [8] [9] [10].

## 6.4 Thermal design decision

Lepton 3.5 provides a practical radiometric development path at 160 by 120 resolution [7]. This resolution may be insufficient for small adjacent parts at the selected working distance. The project must compare at least one higher resolution radiometric module using the same boards and acceptance procedure before the production architecture is frozen.

# 7 Embedded acquisition head

## 7.1 Controller choice

STM32N6570 DK is the recommended development platform because it combines camera interfaces, external memory, display and high speed connectivity in one supported platform [3]. The product may later use a reduced STM32N657 board. An STM32H7 alternative should be considered only if the final RGB interface, compression and transfer rate fit its peripherals.

## 7.2 Firmware modules

| Module | Responsibility |
| --- | --- |
| Device control | Initialization, health monitoring, configuration and error reporting |
| RGB acquisition | Preview, full resolution capture, exposure and focus control |
| NIR acquisition | IR cut control, LED synchronization and NIR exposure |
| Thermal acquisition | VoSPI reception, segment reconstruction and radiometric metadata |
| Timing | Common frame set counter and monotonic timestamps |
| Transport | USB bulk protocol initially, Ethernet as an optional product interface |
| Update | Signed firmware package and recoverable boot process |
| Diagnostics | Sensor status, dropped frames, temperatures and communication statistics |

## 7.3 Communication protocol

Use a documented custom USB bulk protocol rather than treating every stream as a webcam. One control channel configures the head, while framed data packets carry image blocks and metadata. Each packet includes a type, frame set ID, payload length and integrity check. The host confirms configuration changes and records dropped packets.

## 7.4 Prototype hardware

STM32N6570 DK and camera supplied with or compatible with the kit.

FLIR Lepton 3.5 with direct SPI and I2C breakout.

M12 macro lens set and rigid adjustable mount.

White and 850 nm LED boards with constant current drivers.

Time of flight and ambient sensor board.

USB C power and data cables, microSD and a calibration fixture.

# 8 PC software and learning architecture

## 8.1 Software modules

| Layer | Proposed implementation | Responsibility |
| --- | --- | --- |
| Desktop interface | Python and PySide6 for prototype | Live view, inspection projects, corrections and reports |
| Acquisition service | C++ or Python service | Device connection, buffering and frame validation |
| Image processing | OpenCV | Calibration, registration, glare reduction and crops |
| Detection | PyTorch detector | Component bounding boxes and coarse classes |
| OCR | Compact OCR pipeline | Package marking detection and recognition |
| Temporal fusion | CfC or small LNN | Fuse observations and thermal development over time |
| Runtime | ONNX Runtime CUDA | GPU accelerated inference on the target PC |
| Storage | SQLite plus project folders | Metadata, labels, models and raw data |

## 8.2 Recognition pipeline

1.  Correct lens distortion, normalize illumination and register the sensor frames.

2.  Run a component detector on a reduced RGB image.

3.  Extract high resolution component crops from the original RGB and NIR images.

4.  Classify the package and run OCR on normalized crops.

5.  Calculate thermal statistics inside the mapped component region.

6.  Fuse visual, NIR, OCR and thermal sequence features with the temporal model.

7.  Return a class, package, marking candidates, thermal state, confidence and explanation fields.

## 8.3 Role of the LNN

A Liquid Neural Network should not replace the image detector. Liquid Time Constant and closed form continuous time networks are intended for time dependent data [5] [6]. In this system the detector produces component features, while the LNN or CfC model evaluates successive observations, camera movement and temperature change. This separation makes the design easier to train and test.

## 8.4 Controlled learning

The PC application will support three learning levels. Immediate memory stores a confirmed component embedding and label. Incremental training updates a small classification layer using reviewed examples. Full retraining uses the complete dataset and is accepted only after regression testing. Model packages receive a version number, metrics, dataset version and rollback status.

## 8.5 Technician interaction

Confirm a correct class or package.

Replace a wrong result with a supported label.

Enter a manufacturer part number when the marking is known.

Mark a component as unknown without forcing a class.

Record whether a temperature is normal, suspicious or confirmed faulty.

Exclude unusable captures caused by blur, obstruction or incorrect focus.

# 9 Dataset and model development

## 9.1 Initial taxonomy

| Recognition level | Initial classes |
| --- | --- |
| Component class | IC, resistor, capacitor, diode, LED, transistor, MOSFET, inductor, connector, relay and fuse |
| Package | SOT 23, SOT 223, SOIC, TSSOP, QFN, QFP, BGA, TO 220 and common passive sizes |
| Marking | Visible text and symbols with orientation and confidence |
| Thermal condition | Normal, warm, hotspot, fast heating and unknown |

## 9.2 Data collection target

| Data type | Alpha target | Pilot target |
| --- | --- | --- |
| Physical boards | At least 40 | At least 100 |
| Complete board images | 3,000 | 8,000 to 10,000 |
| Annotated component instances | 20,000 | 50,000 or more |
| OCR crops | 5,000 | 20,000 or more |
| Thermal sequences | 300 | 1,000 or more |
| Technician corrections | Exploratory | At least 1,000 reviewed examples |

## 9.3 Dataset rules

Split training, validation and test data by physical PCB, not by image.

Keep raw images and derived crops linked through immutable identifiers.

Record who supplied or reviewed each label and when it changed.

Include blur, glare, dirt, repair residue and partially hidden components.

Balance common and rare classes or report class specific metrics.

Maintain an unknown set containing unsupported and ambiguous parts.

## 9.4 Baseline models

Begin with a supported compact detector such as an ST YOLO or MobileNet SSD family rather than designing a new visual backbone. ST provides STM32N6 object detection examples and model zoo deployment support, although the production inference in this project remains on the PC [4]. Establish the CNN and OCR baselines before adding temporal fusion.

# 10 Calibration and measurement quality

## 10.1 Geometric calibration

Calibrate RGB lens distortion at the selected focus and working distances.

Determine the thermal to RGB transformation using a target visible in both bands.

Store transformations at several distances and interpolate only inside the validated range.

Measure registration error on unseen target positions.

Lock the camera mount after calibration or detect movement that invalidates it.

## 10.2 Illumination calibration

Capture a dark frame and a stable white reference at each spectral channel.

Measure LED output through a photodiode and record LED current and temperature.

Correct nonuniform illumination through flat field calibration.

Reject saturated pixels and exposure settings outside the calibrated range.

## 10.3 Thermal validation

Validate the thermal camera against a traceable reference over the intended PCB temperature range. The product should emphasize relative temperature rise and component comparison unless absolute accuracy has been demonstrated. Emissivity differences between plastics, metals and solder must be documented because shiny surfaces can produce misleading readings.

## 10.4 Calibration assets

| Asset | Purpose |
| --- | --- |
| Printed geometric target | RGB lens and camera geometry |
| Heated dual spectrum target | RGB thermal registration |
| Matte white reference | Visible and NIR normalization |
| Dark cover | Dark frame acquisition |
| Reference thermometer or blackbody | Thermal comparison |
| Golden PCB set | Repeatable end to end regression tests |

# 11 Verification and pilot testing

## 11.1 Verification matrix

| Test | Method | Pass criterion |
| --- | --- | --- |
| Frame synchronization | Record patterned motion and timestamps | All accepted frame sets remain unambiguous |
| RGB image quality | Resolve markings and calibration chart | Defined feature size is readable across working range |
| NIR usefulness | Blind comparison on selected parts | Measurable improvement for at least one priority task |
| Thermal localization | Heat known components | Hot component mapped within target registration error |
| Detector | Unseen PCB test set | Meets class recall and precision targets |
| Unknown handling | Unsupported component set | False identity remains below agreed threshold |
| Learning | Add reviewed corrections and retest | Improvement without unacceptable old class loss |
| Reliability | Four hour capture session | No crash, data corruption or uncontrolled thermal drift |

## 11.2 Pilot protocol

Ten to twenty technicians should use the alpha or beta system on real boards. The pilot compares task completion time, localization success, number of corrections, confidence calibration and user rated usefulness against the technician's normal workflow. Record both successful and failed cases.

## 11.3 Product success criteria

At least 70 percent of pilot users judge the combined view useful enough to use again.

Median fault localization time improves for the selected use cases.

Registration remains within the product target over the calibrated working range.

Supported component recall reaches at least 90 percent on unseen boards.

The system rejects uncertain cases instead of presenting confident false identities.

A credible production cost and selling price are supported by supplier quotations and customer interviews.

# 12 Safety compliance and data protection

## 12.1 Optical safety

NIR and UV illumination require current limits, duty cycle limits, diffusers and enclosure controls. Invisible radiation must not be treated as harmless because users cannot judge intensity by brightness. LED exposure should be evaluated under IEC 62471 [11]. UV illumination, if added, should operate only inside a closed inspection hood or with an equivalent interlock.

## 12.2 Electrical and product compliance

USB powered V1 design with protected power inputs and ESD controls.

EMC pre compliance testing before the custom PCB is frozen.

RoHS compliant components and supplier declarations.

WEEE registration and disposal responsibilities before EU sale.

CE technical documentation, risk assessment and EU declaration for the applicable legislation.

No integrated battery or radio in the first commercial version unless customer research justifies them.

## 12.3 Data protection

PCB images may reveal confidential products. The default application should store projects locally, provide clear export controls and never upload images automatically. Training examples must include their permission status. Shared datasets should remove customer identifiers and confidential board information where possible.

# 13 Work packages schedule and gates

## 13.1 Development schedule

| WP | Work package | Weeks | Output | Gate |
| --- | --- | --- | --- | --- |
| WP 0 | Requirements and user research | 1 to 4 | Problem evidence, use cases and requirements | G0 |
| WP 1 | Acquisition head proof of concept | 3 to 10 | RGB and thermal streaming | G1 |
| WP 2 | NIR illumination and mechanical stand | 7 to 14 | Repeatable RGB and NIR capture | G2 |
| WP 3 | Calibration and data protocol | 11 to 18 | Synchronized registered frame sets | G3 |
| WP 4 | Dataset and baseline detector | 15 to 26 | First validated component detector | G4 |
| WP 5 | OCR package and thermal association | 21 to 32 | Integrated recognition result | G4 |
| WP 6 | LNN and supervised learning | 27 to 38 | Temporal fusion and correction workflow | G5 |
| WP 7 | Alpha application and pilot | 35 to 46 | Field tested alpha | G5 |
| WP 8 | Production feasibility | 43 to 52 | BOM, compliance plan and product decision | G6 |

## 13.2 Team and duration

A two person team covering embedded hardware and PC AI software can target a working pilot in ten to twelve months. A solo development route is more realistically fourteen to eighteen months because data collection, annotation and field validation cannot be compressed safely. Mechanical and compliance work should be supported by specialists when needed.

## 13.3 Gate criteria

| Gate | Decision criterion |
| --- | --- |
| G0 Problem | Users confirm a valuable repair task and acceptable price range |
| G1 Acquisition | Stable RGB and thermal data reach the PC |
| G2 Optics | Required markings and heated parts are observable at the target distance |
| G3 Calibration | RGB, NIR and thermal data are repeatably registered |
| G4 Recognition | Baseline metrics are met on unseen boards |
| G5 Pilot | Technicians demonstrate measurable usefulness |
| G6 Product | Cost, safety, support and demand justify custom hardware |

# 14 Cost plan and market validation

## 14.1 Prototype hardware budget

| Item | Planning range |
| --- | --- |
| STM32N6570 DK | EUR 225 to 250 |
| Lepton 3.5 and breakout | EUR 220 to 320 |
| Macro lens and camera accessories | EUR 60 to 150 |
| White and 850 nm illumination | EUR 50 to 120 |
| Distance and ambient sensors | EUR 25 to 70 |
| Mechanical stand and printed parts | EUR 100 to 300 |
| Calibration fixtures and reference boards | EUR 100 to 300 |
| Cables, power, storage and spare parts | EUR 80 to 180 |
| Practical prototype allowance | EUR 860 to 1,690 |

## 14.2 Development budget

If most engineering is performed by the project owner, a realistic cash budget for the research prototype is approximately EUR 5,000 to 15,000, excluding personal labour. This includes duplicate hardware, PCB revisions, fixtures, pilot units, travel and specialist support. A professionally outsourced commercial programme may require EUR 180,000 to 450,000 depending on dataset work, industrial design, certification and pilot tooling.

## 14.3 Preliminary product economics

| Parameter | Initial planning assumption |
| --- | --- |
| Production quantity | 1,000 units |
| Estimated unit cost | EUR 330 to 500 depending mainly on thermal core |
| Direct sale target | Approximately EUR 899 to 1,199 including VAT |
| Primary customer | Professional PCB repair and electronics service |
| Commercial proof | Paid pilot or preorder from repair professionals |

## 14.4 Market validation questions

Does the system reduce repair time on common no power and overheating faults?

Is component recognition useful without guaranteed exact part numbers?

Would technicians pay more for 256 by 192 thermal resolution?

Is a bench stand preferred over a handheld device for close PCB work?

Which reports or exports are necessary in professional service work?

Is a paid software update or component database acceptable after purchase?

# 15 Risk management

| ID | Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Thermal resolution cannot separate small adjacent parts | High | High | Evaluate higher resolution core before design freeze |
| R2 | RGB thermal parallax causes wrong component assignment | High | High | Fixed stand, distance profiles and acceptance tests |
| R3 | OCR fails on faint or coded markings | High | Medium | Multi angle lighting, NIR capture and ranked results |
| R4 | Training data does not represent real repair boards | High | High | Collect data with pilot users and split by physical board |
| R5 | Continual learning forgets old classes | Medium | High | Replay data, regression suite and rollback |
| R6 | NIR channel adds little practical value | Medium | Medium | Blind task comparison before product commitment |
| R7 | Prototype grows into an unaffordable laboratory system | High | High | Keep V1 scope fixed and gate every spectral option |
| R8 | Customer images contain confidential information | Medium | High | Local processing and explicit dataset permission |
| R9 | Long lead components delay pilot | Medium | Medium | Approve alternatives and buy development spares |
| R10 | Product claims exceed measured accuracy | Medium | High | Publish validated limits and retain unknown output |

## 15.1 Highest priority risk

The highest combined risk is assigning a thermal hotspot to the wrong visible component. This error would undermine the central product promise. The mechanical stand, distance sensing, calibration target and registration test therefore have the same priority as the AI model.

# 16 Immediate actions

## 16.1 First thirty days

1.  Write a one page user interview guide and contact at least ten repair technicians.

2.  Acquire the STM32N6570 DK, Lepton 3.5 interface, macro lens set and initial illumination parts.

3.  Select five representative PCBs including dense smartphone, laptop and industrial boards.

4.  Build a rigid adjustable camera stand with repeatable board positioning.

5.  Create the PC project repository, dataset folder convention and frame set specification.

6.  Stream and save the first RGB image with complete metadata.

7.  Stream and save the first radiometric thermal frame.

8.  Document measured bandwidth, dropped frames, temperatures and image quality.

## 16.2 First technical milestone

The first milestone is complete when the STM32 head sends one synchronized RGB and thermal frame set to the Windows application, the application stores the raw data, and a user can select a visible point and inspect the corresponding thermal region. Recognition and learning begin only after this data path is reliable.

## 16.3 First product milestone

The first product milestone is complete when an external technician can inspect an unfamiliar board, locate a heated part faster than with the technician's existing workflow, correct the component label and reopen the saved inspection without assistance.

# Appendix A Preliminary component taxonomy

| Group | Classes | Notes |
| --- | --- | --- |
| Passive | Resistor, capacitor, inductor and fuse | Exact electrical value only when markings or codes support it |
| Discrete semiconductor | Diode, LED, transistor and MOSFET | Package and marking usually matter more than appearance alone |
| Integrated circuit | Analog, digital, regulator, driver and unknown IC | Start with general IC and add functions after data exists |
| Electromechanical | Relay, switch, button and connector | Large components are useful early classes |
| Board feature | Test point, mounting hole, shield and heatsink | Prevents the detector from treating every visible object as a component |

# Appendix B Model evaluation metrics

| Metric | Purpose |
| --- | --- |
| mAP 50 and mAP 50 to 95 | Object detection accuracy across overlap thresholds |
| Per class precision and recall | Shows weak and strong classes instead of hiding them in an average |
| Character error rate | OCR quality for package markings |
| Unknown false identification rate | Measures whether unsupported parts receive confident wrong labels |
| Expected calibration error | Checks whether confidence values match observed correctness |
| Forgetting score | Measures old class loss after incremental learning |
| Registration error | Distance between known RGB and thermal target coordinates |
| Task completion time | Measures product value in real repair work |

# Appendix C Reference sources

[1] VDI 2220 Product planning flow terms and organization. VDI. https://www.vdi.de/en/home/vdi-standards/details/vdi-2220-product-planning-flow-terms-and-organization

[2] VDI 2221 Part 1 Design of technical products and systems. VDI. https://www.vdi.de/en/home/vdi-standards/details/vdi-2221-blatt-1-design-of-technical-products-and-systems-model-of-product-design

[3] STM32N6570 DK product page and board features. STMicroelectronics. https://www.st.com/en/evaluation-tools/stm32n6570-dk.html

[4] STM32 AI Model Zoo Services object detection documentation. STMicroelectronics. https://github.com/STMicroelectronics/stm32ai-modelzoo-services

[5] Hasani R et al. Liquid Time constant Networks. AAAI 2021. https://ojs.aaai.org/index.php/AAAI/article/view/16936

[6] Hasani R et al. Closed form continuous time neural networks. Nature Machine Intelligence 2022. https://www.nature.com/articles/s42256-022-00556-7

[7] Lepton radiometric LWIR camera family. Teledyne FLIR OEM. https://oem.flir.com/developer/lepton-family/

[8] IMX487 ultraviolet image sensor. Sony Semiconductor Solutions. https://www.sony-semicon.com/en/products/is/industry/uv.html

[9] SenSWIR 400 to 1700 nm image sensor technology. Sony Semiconductor Solutions. https://www.sony-semicon.com/en/technology/industry/senswir.html

[10] C12880MA miniature spectrometer. Hamamatsu Photonics. https://www.hamamatsu.com/jp/en/product/optical-sensors/spectrometers/mini-spectrometer/C12880MA.html

[11] IEC 62471 Photobiological safety of lamps and lamp systems. IEC. https://webstore.iec.ch/en/publication/7076

[12] CE marking and EU product requirements. European Commission. https://single-market-economy.ec.europa.eu/single-market/goods/ce-marking_en

Source pages and indicative market prices were checked on 22 September 2026. All cost figures in this document are planning estimates and require supplier quotations before purchasing or commercial commitment.